[Your Country]

[Your Organization]

Project Management Guideline & Handbook

Version 1.0

2026

This handbook provides an overall understanding of how to manage and deliver projects successfully in the [Your Organization]. It sets out the framework, roles, procedures, and templates followed across the full project lifecycle — from idea to closure — as a practical reference for everyone involved in a project. It aligns with the Project Management Institute (PMI) standard in the PMBOK Guide and draws entirely on the package's own documents and templates.

# 1. The Project Management Cycle

Projects are divided into five process groups that simplify management and steer the work in the best direction. These are the PMI process groups.

| Process Group | Purpose |
| --- | --- |
| Initiating | Authorize the project and define it at a high level |
| Planning | Establish the baselined plan across all knowledge areas |
| Executing | Produce the deliverables and coordinate people and resources |
| Monitoring & Controlling | Track performance and govern changes against the baseline |
| Closing | Finalize, hand over, and capture lessons |

# 2. Project Governance

| Role | Responsibility |
| --- | --- |
| Steering Committee | Approves initiation and funding, approves stage gates and change requests, and resolves escalated decisions |
| Sponsor | Accountable for overall success; secures funding; approves the charter and scope; appoints the PM; evaluates success at completion |
| PMO | Sets the method, standards, and templates; oversees initiation; assures quality; tracks risks; reports the portfolio to leadership |
| Project Manager | Leads planning and delivery; manages scope, schedule, budget, risk, and stakeholders; reports progress; coordinates team and vendors |
| Project Team | Carries out project activities with the required skills, drawn from across departments and engaged specialists |
| Business Owner | Owns the business case and requirements; accepts deliverables; owns and tracks the benefits |

# 3. Project Processes and Procedures

This section walks through each phase of the project: a short description of what happens, and the templates used — their purpose, content, who prepares each, and who approves it.

## 3.1 Initiation

A project begins when an idea is submitted to the Steering Committee for approval. The submission states the need and expected impact, the outline scope and deliverables, the alignment with strategy, and a preliminary feasibility view, so the committee can make an informed decision. The idea is first classified by size and risk to set the right level of governance, and the case for investment is captured in the Business Case. Once approved, a Sponsor and Project Manager are assigned, and the Project Manager prepares the Project Charter — the document that authorizes the project and serves as its reference throughout.

| Template | Purpose | Content | Prepared by | Approved by |
| --- | --- | --- | --- | --- |
| Project Classification | Classify the initiative to set its governance | Criteria, weighting, score, resulting tier | PMO | Sponsor |
| Business Case | Decide if the project is worth the investment | Background, options, cost/benefit, recommendation, risks | Business Owner | Steering Committee |
| Project Charter | Formally authorize the project | Purpose, objectives, scope, milestones, budget, risks, approval | Project Manager | Sponsor |

## 3.2 Planning

After authorization, the project is planned in detail. The scope and acceptance criteria are defined, requirements are captured, responsibilities are assigned with a RACI matrix, stakeholders and communication are planned, risks are registered with responses and owners, and the benefits to be realized are made measurable. Together these form the baseline against which delivery is tracked, and they address the ten knowledge areas of the PMI standard — scope, schedule, cost, quality, resources, communications, risk, procurement, stakeholders, and the integration that holds them together.

| Template | Purpose | Content | Prepared by | Approved by |
| --- | --- | --- | --- | --- |
| Scope of Work | Define scope and acceptance | In/out of scope, deliverables, assumptions, acceptance criteria | Project Manager | Sponsor |
| Business System Requirements | Capture detailed requirements | Functional and non-functional requirements | Project Manager | Business Owner |
| RACI Responsibility Matrix | Assign responsibilities | Activities mapped to roles (R/A/C/I) | Project Manager | Sponsor |
| Stakeholder Register & Communication Plan | Engage stakeholders and plan communication | Stakeholders, influence, strategy, communication matrix | Project Manager | Sponsor |
| Risk Log | Identify and manage risk | Risk, likelihood, impact, response, owner | Project Manager | — |
| Benefits Realization Plan | Define and track benefits | Benefit, measure, baseline, target, owner, timing | Business Owner | Sponsor |

## 3.3 Execution

Execution produces the deliverables. The Project Manager confirms readiness, leads the team and any vendors, and ensures each deliverable is produced and accepted against its criteria. Issues are logged and worked to resolution. Where a change to scope, cost, or deliverables is needed, it is not made silently — a Change Request is raised, assessed for impact, and approved through governance before the work proceeds.

| Template | Purpose | Content | Prepared by | Approved by |
| --- | --- | --- | --- | --- |
| Issue Log | Track and resolve issues | Issue, owner, priority, status, resolution | Project Manager | — |
| Change Request Log | Request and control changes | Change, impact, decision, status | Project Manager | Steering Committee |

## 3.4 Monitoring & Control

Monitoring runs alongside execution to keep scope, schedule, cost, quality, and risk under control. A status report is issued on a regular cadence so progress against the plan is clear, and a consolidated dashboard gives leadership a high-level view across the portfolio. Decisions are governed through change control and stage-gate reviews, with escalation as needed.

| Template | Purpose | Content | Prepared by | Approved by |
| --- | --- | --- | --- | --- |
| Project Status Report | Provide scheduled status updates | Scope/schedule/budget status, achievements, risks | Project Manager | — |

Illustrative consolidated dashboard the PMO provides to report portfolio status to leadership:

| Project | Health | Schedule | Scope | Budget | PM | Go-live |
| --- | --- | --- | --- | --- | --- | --- |

## 3.5 Closing

Every project closes formally. The Project Manager confirms that the deliverables are accepted and handed over to operations, demonstrates the results against the targets that justified the project, captures the lessons learned for future projects, and obtains the closure sign-off. Benefits tracking is handed to the benefit owner to continue after the project ends.

| Template | Purpose | Content | Prepared by | Approved by |
| --- | --- | --- | --- | --- |
| Lessons Learned & Project Closure Log | Capture lessons, confirm acceptance, and close | Lessons (category, impact, recommendation), closure checklist, sign-off | PM & Team | Steering Committee |

# 4. Communication Plan

The PMO maintains a regular communication and reporting cadence across the lifecycle, with escalation as needed per the governance plan.

| Forum | Cadence | Audience |
| --- | --- | --- |
| Project status report | Weekly | PM → Sponsor & PMO |
| Portfolio review | Monthly | PMO → Steering Committee |
| Stage-gate / governance review | At each gate | Steering Committee |
| Escalation | As needed | Per the governance plan |

# 5. Appendix: Templates

This appendix contains the full, fill-in templates, ordered by project phase. Each template is also provided as a standalone file within the package folders.

## 5.1 Initiation Templates

Project Classification

## General Information

| Project Name | Enter the project name |
| --- | --- |
| Sponsoring Entity | Enter the sponsoring entity |
| Date | Enter the date |

## Classification Criteria

Score each criterion from 1 (low) to 4 (high), apply the weight, then total.

| Criterion | Weight | Score (1–4) | Result |
| --- | --- | --- | --- |
| Strategic impact |  |  |  |
| Budget size |  |  |  |
| Duration |  |  |  |
| Complexity |  |  |  |
| Risk level |  |  |  |

## Resulting Classification

| Classification | ☐ Low ☐ Medium ☐ High ☐ Strategic |
| --- | --- |

Business Case

## General Information

| Project Name | Enter the project name |
| --- | --- |
| Requester | Enter the requester name |
| Date | Enter the date |
| Beneficiary | Enter the beneficiary |
| Sponsoring Entity | Enter the sponsoring entity |

## Background & Context

Describe the current situation and the need or challenge the project addresses.

## Problem / Opportunity

State the problem to solve or the opportunity to capture.

## Beneficiaries

| Beneficiaries | ☐ Employees ☐ Departments ☐ Partners ☐ Clients ☐ Other |
| --- | --- |

## Strategic Alignment

Explain how the project supports the office's strategic objectives.

## Options Considered

| Option | Description | Pros & Cons |
| --- | --- | --- |

## Cost / Benefit Analysis

| Item | Cost | Benefit |
| --- | --- | --- |

## Complexity

| Complexity | ☐ High ☐ Medium ☐ Low |
| --- | --- |

## Recommendation

State the final recommendation and its justification.

## Risks

| Risk | Response |
| --- | --- |

## Approval

| Role | Name | Signature & Date |
| --- | --- | --- |
| Business Owner |  |  |
| Steering Committee |  |  |

Project Charter

## General Information

| Project Name | Enter the project name |
| --- | --- |
| Sponsoring Entity | Enter the sponsoring entity |
| Project Owner | Enter the project owner |
| Project Manager | Enter the project manager |
| Client / Entity | Enter the client or entity |
| Date | Enter the date |
| Version | e.g. 1.0 |

## Purpose & Justification

State why the project exists and the value it delivers.

## Objectives & Success Criteria

| Objective | Measurable Outcome |
| --- | --- |

## Scope

| In Scope | Out of Scope |
| --- | --- |

## Key Deliverables

| Deliverable | Delivery Date |
| --- | --- |

## Milestones

| Milestone | Description | Date |
| --- | --- | --- |

## Estimated Budget

| Item | Amount |
| --- | --- |

## Key Risks

| Risk | Mitigation |
| --- | --- |

## Project Team

| Name | Role | Department |
| --- | --- | --- |

## Approval

| Role | Name | Signature & Date |
| --- | --- | --- |
| Sponsor |  |  |
| Project Manager |  |  |

## 5.2 Planning Templates

Scope of Work

## General Information

| Project Name | Enter the project name |
| --- | --- |
| Project Manager | Enter the project manager |
| Client / Entity | Enter the client or entity |
| Date | Enter the date |

## Purpose

Summarize the purpose of the work.

## Scope

| In Scope | Out of Scope |
| --- | --- |

## Deliverables

| Deliverable | Description |
| --- | --- |

## Assumptions & Constraints

| Assumptions | Constraints |
| --- | --- |

## Acceptance Criteria

Acceptance Criterion

## Approval

| Role | Name | Signature & Date |
| --- | --- | --- |
| Sponsor |  |  |

Business System Requirements

## General Information

| Project Name | Enter the project name |
| --- | --- |
| Project Manager | Enter the project manager |
| Project Owner | Enter the project owner |
| Date | Enter the date |

## Project Summary

Briefly describe the system or business need.

## Objectives

Objective

## Functional Requirements

List each requirement with a unique ID and a priority (High / Medium / Low).

| ID | Requirement | Priority |
| --- | --- | --- |

## Non-functional Requirements

| ID | Requirement |
| --- | --- |

## Approval

| Role | Name | Signature & Date |
| --- | --- | --- |
| Business Owner |  |  |

RACI Responsibility Matrix

## General Information

| Project Name | Enter the project name |
| --- | --- |
| Date | Enter the date |

## Matrix

Enter R, A, C, or I in each cell for every activity.

| Activity / Deliverable | Owner | Sponsor | Committee | PM | Team |
| --- | --- | --- | --- | --- | --- |

## Legend

R Responsible  ·  A Accountable  ·  C Consulted  ·  I Informed

Stakeholder Register & Communication Plan

## General Information

| Project Name | Enter the project name |
| --- | --- |
| Date | Enter the date |

## Stakeholder Register

Rate influence and interest as High / Medium / Low.

| Stakeholder | Role | Influence | Interest | Engagement Strategy |
| --- | --- | --- | --- | --- |

## Communication Plan

| Message | Audience | Channel | Frequency | Owner |
| --- | --- | --- | --- | --- |

Risk Log

## General Information

| Project Name | Enter the project name |
| --- | --- |
| Date | Enter the date |

## Log

Rate likelihood and impact (e.g. High/Medium/Low); the rating combines them.

| ID | Risk | Likelihood | Impact | Rating | Response | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |

Benefits Realization Plan

## General Information

| Initiative Name | Enter the initiative name |
| --- | --- |
| Date | Enter the date |
| Version | e.g. 1.0 |
| Prepared by | Enter your name |

## Benefit Profile

Make each benefit measurable: a baseline, a target, and a date.

| Benefit | Measure | Baseline | Target | Owner | Timing |
| --- | --- | --- | --- | --- | --- |

## Realization Plan

| Activity | Owner | Date |
| --- | --- | --- |

## 5.3 Execution Templates

Issue Log

## General Information

| Project Name | Enter the project name |
| --- | --- |
| Date | Enter the date |

## Log

Record every issue, its owner, and its resolution.

| ID | Description | Date Raised | Owner | Priority | Status | Resolution |
| --- | --- | --- | --- | --- | --- | --- |

Change Request Log

## General Information

| Project Name | Enter the project name |
| --- | --- |
| Date | Enter the date |

## Log

No scope, cost, or deliverable changes without a logged, approved request.

| ID | Description | Date | Requester | Impact | Decision | Status |
| --- | --- | --- | --- | --- | --- | --- |

## 5.4 Monitoring & Control Templates

Project Status Report

## General Information

| Project Name | Enter the project name |
| --- | --- |
| Reporting Period | e.g. Week / Month |
| Date | Enter the date |
| Prepared by | Enter your name |

## Overall Status

| Overall status | ☐ On Track ☐ Some issues ☐ Severe issues |
| --- | --- |

## Status Summary

| Area | Status | Notes |
| --- | --- | --- |
| Scope |  |  |
| Schedule |  |  |
| Budget |  |  |
| Risks |  |  |

## Achievements this Period

Achievement

## Planned for next Period

| Activity | Date |
| --- | --- |

## Key Risks & Issues

| Item | Impact | Action |
| --- | --- | --- |

## 5.5 Closing Templates

Lessons Learned & Project Closure Log

## General Information

| Project Name | Enter the project name |
| --- | --- |
| Sponsoring Entity | Enter the sponsoring entity |
| Project Owner | Enter the project owner |
| Project Manager | Enter the project manager |
| Client / Entity | Enter the client or entity |
| Date | Enter the date |
| Version | e.g. 1.0 |

## Lessons Learned

| Category | What happened | Impact | Recommendation |
| --- | --- | --- | --- |

## Closure Checklist

| Item | Complete? | Notes |
| --- | --- | --- |
| Deliverables accepted |  |  |
| Handover to operations done |  |  |
| Documentation updated |  |  |
| Benefits handed to owner |  |  |

## Project Manager Confirmation

| I confirm | ☐ Assessed the deliverables ☐ Communicated to stakeholders ☐ Arranged the handover |
| --- | --- |

## Sign-off

| Role | Name | Signature & Date |
| --- | --- | --- |
| Project Manager |  |  |
| Sponsor |  |  |
| Steering Committee |  |  |

# 6. References

This guideline aligns with, and references, the following professional standards (not reproduced):

•  Project Management Institute (PMI), A Guide to the Project Management Body of Knowledge (PMBOK® Guide).

•  PMI, The Standard for Project Management.