## PfMP
Maturity Level | Process perspective | Attributes | Assessments %
Level-1 | 1-Management control | The organization recognizes the portfolio, but has little or no documented processes or standards for its management, and a limited directory of programmes and projects. The recognition of a corporate or departmental portfolio by the organization is a significant step usually associated with the investment control or business-case approval process. It is an important first step towards PPM maturity because, by articulating the portfolio, the organization sets out its criteria for prioritization and oversight. | 0%
Level-1 | 2-Benefits management | There is a recognition that programmes and projects exist within the corporate portfolio to enable the achievement of benefits for the organization. However, this will not translate into a defined benefits management process. | 0%
Level-1 | 3-Financial management | Portfolio oversight of programmes and projects may be recognized but there is little or no corporate investment control. There is some financial control but it is often left to budget centres to approve and control programmes and projects according to their own criteria. | 0%
Level-1 | 4-Stakeholder management | The portfolio may be acknowledged, but there is little or no connection between programme and project output, and business outcome and benefits. | 0%
Level-1 | 5-Risk management | There is a growing recognition that risks need to be managed and that, at least for key business initiatives (e.g. cost saving, major site developments), risks threaten success. There is risk identification (probably in different systems, e.g. spreadsheets, text documents, databases etc.) and maybe some quantification of risk, but little actual management of risk. | 0%
Level-1 | 6-Organizational governance | The organization has some inconsistent and informal attempts to align individual programmes and projects with corporate objectives, and there is an ad hoc, inconsistent and ineffective oversight of programmes and projects. | 0%
Level-1 | 7-Resource management | Programme and project resource requirements are recognized but not systematically managed. Resources are planned, developed and allocated on an ad hoc and, usually, project basis. The symptoms of not having a portfolio approach to resource identification and allocation are all too obvious, but the organization has yet to fully commit to undertake robust corporate portfolio management. | 0%
Level-2 | 1-Management control | There are some pockets of portfolio discipline within individual departments, but this is based on key individuals rather than implemented as a comprehensive and consistent organization-wide approach. The concepts of portfolio management will have been grasped by some and indeed there may be local experts. Work will be ongoing to establish a portfolio management approach across the organization through the recognition of an investment cycle, e.g. proposition, feasibility, design, implementation, review etc. Improved business-case definition is enabling programmes and projects to be tested against the corporate objectives and priorities. | 0%
Level-2 | 2-Benefits management | The development of the investment cycle will be increasing the awareness and importance of identifying benefits and subsequently tracking whether they have been achieved. However, the realization of benefits is still likely to be patchy, inconsistent and not monitored. | 0%
Level-2 | 3-Financial management | There are some pockets of good business-case production and some, usually departmental, structures to oversee investment decisions. However, business cases are often appraised independently of each other, and real corporate priorities have not been established. Reasonable financial control, business-case production, procurement appraisal, and investment control are restricted to individuals and departments. | 0%
Level-2 | 4-Stakeholder management | A portfolio of programmes and projects that serve the corporate objectives and priorities is increasingly seen as the driving force for approval, oversight and performance management. The portfolio is tending to be driven by individual programmes and projects, i.e. bottom up. | 0%
Level-2 | 5-Risk management | The increasing awareness that the organization bears corporate risk tends to lead to a top-down (perhaps ‘knee-jerk’) approach to identifying portfolio risk (focusing on major corporate initiatives) that is unconnected to the bottom-up identification of risks in programmes and projects. This often leads to duplication of effort, competing teams, non-optimal allocation of funding, inconsistency and, therefore, the ineffective management of corporate risk. | 0%
Level-2 | 6-Organizational governance | Some attempts are made to recognize the portfolio of programmes and projects, but there is still no overall leadership and direction for the process. Programmes and projects may be initiated and run without full regard to the corporate goals, priorities and targets. It is difficult to establish the rationale for which programmes and projects are funded or approved. | 0%
Level-2 | 7-Resource management | The organization has started to develop resource management processes and improve the identification and allocation of resources to specific initiatives. However, this is likely to be reliant on key individuals and does not assess the impact of resource allocation against the wider portfolio. The problems of not managing resources across the portfolio will be better understood and solutions are starting to be developed in isolated programmes or departments. | 0%
Level-3 | 1-Management control | Standard portfolio management processes, as well as roles and responsibilities for governance and delivery, are defined, documented and understood. Corporate portfolio management processes have specified owners and there is evidence of use and effectiveness of a portfolio management office. Planning and reporting tools are implemented and used effectively, and portfolio guidelines exist and are actively used. Portfolio management is both defined and established across the organization, and defined processes are being used to reduce and manage corporate risk. | 0%
Level-3 | 2-Benefits management | A centrally managed framework is used to define and track the delivery of benefits across the business operations. | 0%
Level-3 | 3-Financial management | There will be established standards for the investment management process and the preparation of business cases. The costs, expenditure and forecasts will be monitored at portfolio level in accordance with organizational guidelines and procedures. There will be defined interfaces with other financial functions within the organization. Portfolio financial management is defined and established across the organization, and defined processes are being used to improve investment and procurement decisions, and monitor programme and project budgets. | 0%
Level-3 | 4-Stakeholder management | Stakeholder management in the portfolio and individual programmes and projects is taken seriously and genuine authority is extended to appropriate stakeholders. The investment cycle is fully functioning and drives entry to the portfolio, and the importance of business-process design is recognized. The portfolio is tending to drive individual programmes and projects, i.e. top down. | 0%
Level-3 | 5-Risk management | Portfolio risks are identified and quantified, and mitigation plans developed and funded. Risks across the portfolio are continually reviewed and there is reporting to senior management. Robust risk management includes: the identification of strategic, delivery and operational risks; the consistent analysis of risk in terms of probability, impact (on project schedule, cost and quality of deliverable) and timing; the production and funding of contingency plans; and the continual review by knowledgeable experts, risk owners and senior managers. | 0%
Level-3 | 6-Organizational governance | The principles of portfolio, programme and project management are widely understood, practised to a consistent standard, and underpin the governance framework. | 0%
Level-3 | 7-Resource management | Programme and project resources are being managed within defined and well-used processes. This allows the organization to increase the targeting and development of resources against corporate objectives. The competent identification of the required resources, skills and experience (especially in the business as distinct from the project team) enables the organization to improve the likelihood of committed resources being released in a timely manner to support the work of programmes and projects. | 0%
Level-4 | 1-Management control | Portfolio management processes are integrated with those of programme and project management, with programme and project performance capability metrics in place and used. | 0%
Level-4 | 2-Benefits management | The benefits management process is well established and is integrated into how the organization manages itself. | 0%
Level-4 | 3-Financial management | The organization has effective and robust financial control of its investment decisions and the approval and monitoring of programmes and projects. There is proactive, evidence-based management of the portfolio. Financial oversight of the portfolio is corporate-centric rather than programme- or project-centric. | 0%
Level-4 | 4-Stakeholder management | The organization, as part of the initial planning, readiness preparation and deployment planning, consistently ascertains the current organizational culture and determines the climate and activities required to improve the effectiveness of business change and the generation of ideas. Business areas fully own the transition to new ways of working and, via the corporate portfolio, see programmes and projects as suitable vehicles to effectively manage that transition. | 0%
Level-4 | 5-Risk management | The organization’s appetite for risk, and the balance of risk and benefit across the portfolio, are continually reviewed and managed. Senior managers own and oversee the management of risks across the portfolio. Portfolio risk management is embedded within the corporate reporting and management structures. | 0%
Level-4 | 6-Organizational governance | All programmes and projects are integrated into an achievable portfolio aligned with corporate objectives and strategic targets. | 0%
Level-4 | 7-Resource management | The organization has established effective capacity and capability strategies and processes for obtaining, allocating and adjusting resource levels (including people, funding, estate and tools) in line with medium-term and long-term investment plans. | 0%
Level-5 | 1-Management control | Potential problems in the programme and project management context are identified and prevented from occurring. There is an awareness of the likely potential and impact of new technology being embedded into the standard programme and project management processes. Quantitative and qualitative measures, and lessons, are being routinely used to improve the effectiveness of corporate portfolio management. | 0%
Level-5 | 2-Benefits management | Benefits management is integral to the development and maintenance of the business strategy. | 0%
Level-5 | 3-Financial management | Financial control of the portfolio is an integral part of the organization’s financial control regime. Appropriate financial control is embedded within programmes and projects, and integrated with that for the organization. | 0%
Level-5 | 4-Stakeholder management | Continual business-process improvements are undertaken in a planned manner, aligned with corporate objectives and priorities, with demonstrable benefits and measurement of the efficacy of programmes and projects. The portfolio, programmes and projects are viewed as the preferred instruments to achieve continual improvement in the organization’s business processes. | 0%
Level-5 | 5-Risk management | The process of portfolio risk management is continually improved, based on analysis of evidence from within the organization and comparison with other organizations. The corporate risk management process is continually improved, and the corporate risk model is refined to align with the organizational culture and corporate objectives. | 0%
Level-5 | 6-Organizational governance | The portfolio is proactively managed to ensure that it remains sufficiently dynamic and agile to cater for changes in business direction and priorities. The portfolio is supporting the organization’s goals by its use of performance measures, improving quality and productivity, and the effective use of the organization’s assets. The governance of investment management has moved from a programme- or project-centric process to a corporate-centric process. | 0%
Level-5 | 7-Resource management | The analysis and management of the portfolio drives the planning, development and allocation of programme and project resources to ever improve the effective use of resources in achieving the corporate objectives. | 0%

## PfMP (Result)
PfM3 Model - Assessment Chart
Maturity Level | [7 empty] | Summary
Level 5 | [7 empty] | 0%
Level 4 | [7 empty] | 0%
Level 3 | [7 empty] | 0%
Level 2 | [7 empty] | 0%
Level 1 | [7 empty] | 0%
Process Perspectives
Fully Meets | Management Control | Benefits management | Financial management | Stakeholder management | Risk management | Organizational Governance | Resource management | PfM3 Final Assessment
Partially Meets | [7 empty] | Organization at PfM3 Maturity Level
Never Meets | [7 empty] | 0%

## PgMP
Maturity Level | Process perspective | Attributes | Assessments %
Level-1 | 1-Management control | The programme management terminology may be in use but will be used inconsistently. The general approach will be based on project rather than programme level. | 0%
Level-1 | 2-Benefits management | There is recognition of the concept of benefits that can be differentiated from project outputs. Benefits will be developed at a project level with minimal programme control. | 0%
Level-1 | 3-Financial management | There are minimal or no financial controls; those that exist are principally related to projects. | 0%
Level-1 | 4-Stakeholder management | Programme management is principally seen as an area of activity outside the remit of business operations. Managers may see the programme approach as threatening rather than adding value. | 0%
Level-1 | 5-Risk management | There is minimal evidence of risk management being deployed to any beneficial effect; the main focus is on issue management. | 0%
Level-1 | 6-Organizational governance | Informal governance of programmes exists but has undefined linkage to projects and the broader organizational controls. Roles are likely to be notional. | 0%
Level-1 | 7-Resource management | The focus is on the project resources being deployed, with minimal focus on programme management resource requirements. | 0%
Level-2 | 1-Management control | There is general understanding of the concepts of programme management. There is evidence of good examples of deployment but there will be inconsistency and varying levels of commitment. There is a strategic acknowledgement of the value of programme management. | 0%
Level-2 | 2-Benefits management | Benefits are recognized as a key element and differentiating factor for programmes. The focus is likely to be at the project level but initial evidence exists of tracking at a programme level. There will be more detailed definition of benefits. | 0%
Level-2 | 3-Financial management | Financial approvals for projects are evident but the cost of the programme is not being fully accounted for in all cases. | 0%
Level-2 | 4-Stakeholder management | Operational and business staff are involved with the programme and engaging with the delivery. Engagement is consultative and reactive rather than decision-making. | 0%
Level-2 | 5-Risk management | Risk management is recognized and used on programmes, but there are inconsistencies in approach, commitment and deployment. | 0%
Level-2 | 6-Organizational governance | Programme management is beginning to take shape but with ad hoc controls being applied and no clear strategic control. Roles and responsibilities will be unclear, as will reporting lines. | 0%
Level-2 | 7-Resource management | Resources are being deployed across the organization but there is little evidence of a consistent approach to acquisition, planning or management. | 0%
Level-3 | 1-Management control | There is a consistent approach to programme management controls, with the application of approaches in all programmes. A defined lifecycle exists and there is active management and application of controls to programmes within it. | 0%
Level-3 | 2-Benefits management | A centrally managed framework is used to define and track the delivery of benefits across the business operations. | 0%
Level-3 | 3-Financial management | There are standard approaches to financial management and cost assessments that are tracked through the lifecycle and are deployed consistently across all programmes. | 0%
Level-3 | 4-Stakeholder management | There is organization and business engagement with the programme approach. There is active and regular input into the way programmes are managed, with the major focus on the achievement of business change rather than programme delivery. | 0%
Level-3 | 5-Risk management | Risk management has a clearly defined process that is followed consistently by all programmes. The framework is based on industry standards and is supported by a toolkit. | 0%
Level-3 | 6-Organizational governance | All roles and responsibilities are documented within terms of reference. Strategic controls are applied consistently, with decision-making structures in place. | 0%
Level-3 | 7-Resource management | There is planned deployment and effective utilization of resources across the programme, supported by standard approaches to planning and tracking. | 0%
Level-4 | 1-Management control | Programme management is seen by the board as a key tool for the delivery of strategic objectives. There is acceptance of a common approach, which is supported by management behaviour. Within the programme environment the focus is on improvement, adoption and measurement. | 0%
Level-4 | 2-Benefits management | Benefits management is embedded within the programme management approach and underpins the justification and management of each programme. | 0%
Level-4 | 3-Financial management | Programme lifecycles are being flexed effectively to manage the availability of finance, and effective decision-making is occurring on the basis of financial evidence. | 0%
Level-4 | 4-Stakeholder management | There is extensive engagement with business operations, with an equal focus on business and organization improvement and programme delivery. | 0%
Level-4 | 5-Risk management | Risk management works effectively, with active management and avoidance of risks being evident and embedded behaviours. | 0%
Level-4 | 6-Organizational governance | Clearly aligned decision-making processes adopt and integrate the broader organizational governance and are transparent to those involved. Programme management responsibilities are embedded within broader role descriptions. | 0%
Level-4 | 7-Resource management | There is measurement of resource utilization, proactive engagement to raise and broaden capability, and evidence of a resulting improvement in delivery. | 0%
Level-5 | 1-Management control | There is integration between a programme approach and the delivery of strategic aims and objectives. Programme management is accepted throughout the organization as the optimal approach to strategic delivery. | 0%
Level-5 | 2-Benefits management | Benefits management is embedded within the organizational approach to change and benefits are assessed as part of the development of corporate strategies. | 0%
Level-5 | 3-Financial management | Financial control is evident throughout the programme lifecycle and a balanced view of risk taking is underpinning the programme governance. | 0%
Level-5 | 4-Stakeholder management | Business operations are integral to the design and delivery of effective programmes. Management methods are integrated within the programme framework. Programme management is seen as the route to business change and improvement. | 0%
Level-5 | 5-Risk management | Risk management is embedded in the organizational culture and underpins all decision-making within the programme. | 0%
Level-5 | 6-Organizational governance | Programme management is embedded at board level, with clear ownership and control responsibilities embedded within individual directors’ terms of reference. | 0%
Level-5 | 7-Resource management | Resources are deployed optimally; there is clear evidence of balancing internal and external expertise, and knowledge is being embedded into the business. | 0%

## PgMP (Result)
PgM3 Model - Assessment Chart
Maturity Level | [7 empty] | Summary
Level 5 | [7 empty] | 0%
Level 4 | [7 empty] | 0%
Level 3 | [7 empty] | 0%
Level 2 | [7 empty] | 0%
Level 1 | [7 empty] | 0%
Process Perspectives
Fully Meets | Management Control | Benefits management | Financial management | Stakeholder management | Risk management | Organizational Governance | Resource management | PgM3 Final Assessment
Partially Meets | [7 empty] | Organization at PgM3 Maturity Level
Never Meets | [7 empty] | 0%

## PjMP
Maturity Level | Process perspective | Attributes | Assessments %
Level-1 | 1-Management control | Project management terminology is being used by some within the organization but not in a consistent manner and indeed without it being understood by all stakeholders. Some projects will be defined, conducted and managed to some extent. Where projects have been defined, the scope and objectives may be articulated to a wider audience with the aim of achieving commitment and support. | 0%
Level-1 | 2-Benefits management | There is recognition of the concept of benefits that can be differentiated from project outputs. Benefits may be cited within some project documentation but will tend to be qualitative or intangible. There will be limited, if any, responsibility for benefits planning and realization. The organization will have difficulty in reviewing benefits and attributing them to projects. | 0%
Level-1 | 3-Financial management | There are minimal financial controls at the project level and a general lack of accountability for monitoring project expenditure. The lack of formal business cases will present some difficulties for the organization in fully appraising potential projects, making investment decisions and directing such investments. | 0%
Level-1 | 4-Stakeholder management | Project management process improvement will be unplanned. There will be evidence of some ‘fire-fighting’, with experienced managers perhaps being used to rescue projects in difficulty. The project management process is likely to be chaotic and therefore in need of some basic standardization and established baselines on which to consider improvement. | 0%
Level-1 | 5-Risk management | There is minimal evidence of risk management being deployed to any beneficial effect. A risk management process will not have been established, although some projects will be cognizant of some of the risks that threaten them and these may be documented in an inconsistent manner within project risk registers. There will be little evidence of these registers being maintained. | 0%
Level-1 | 6-Organizational governance | Informal governance of projects exists but has undefined linkage to the broader organizational controls. Project roles are likely to be notional and terms of reference for the governance structures are unlikely to be fully documented. Planning for business review and governance checkpoints is unlikely to be fully developed. Leadership and responsibilities may not be fully attributable. | 0%
Level-1 | 7-Resource management | There is little recognition of the skills and competencies needed to deliver projects successfully. As projects are poorly defined, the role of project manager is compromised; project managers are unlikely to have the support and commitment of the organization, or the resources needed to accomplish project objectives in a consistent and planned manner. | 0%
Level-2 | 1-Management control | The concepts of project management will have been grasped by some within the organization and indeed there may be local experts, e.g. experienced project managers working within the organization on key projects. Work will be ongoing to establish a project management approach across the organization through the recognition of a project lifecycle, supported by document templates and some tools and techniques. Such initiatives are likely to be championed by the experienced project managers. | 0%
Level-2 | 2-Benefits management | Benefits are recognized within project business cases. There will be some documentation on who is responsible for particular benefits and their realization, but this is unlikely to be followed through. The difference between outputs, outcomes and benefits will be understood by most managers within the organization. The role of senior responsible owner (SRO) in benefits management and realization may be articulated on some projects. Post-implementation reviews (post-project reviews) will be focused on the project activities and deliverables. | 0%
Level-2 | 3-Financial management | Business cases are being produced in various forms and the better or more formal cases will present the project rationale on which to obtain organizational commitment to the project and take an investment decision. Financial management of projects will be variable, depending primarily on the competency of the project manager. There will be little, if any, evidence that cost considerations are used in, for example, contingency planning and risk evaluation. | 0%
Level-2 | 4-Stakeholder management | Project management process development and improvement actions are not necessarily planned across the whole organization. Strengths and weaknesses will be identified by project managers in isolation and action taken to address specific weaknesses. Project management will be assessed at the local level by individual managers, and some improvements will be initiated. There will be little dissemination of good practice between projects and little central control of the improvement agenda. | 0%
Level-2 | 5-Risk management | Risk management is recognized and used on all projects, but there are likely to be inconsistencies in approach, commitment and deployment. Key project managers will understand and articulate the purpose and importance of risk management, but there will not be the same level of commitment and understanding across all projects and throughout the organization generally. There will be inconsistencies in the reporting and escalation of risks from projects to other stakeholders within the organization. | 0%
Level-2 | 6-Organizational governance | Project management from an organizational perspective is beginning to take shape but with ad hoc controls being applied and with no clear strategic control. Roles and responsibilities are sometimes unclear, as are reporting lines and accountabilities. Some projects are perceived as falling outside of the organizational governance arrangements. There is little effective analysis and management of stakeholder groupings or management of their expectations. | 0%
Level-2 | 7-Resource management | Resources are being deployed on projects, but there is little evidence of a consistent approach to acquisition, planning or management of these resources. The organization has started to adopt formal project management methods and perceives the need to familiarize staff with the methods, tools and techniques that are being adopted. Appropriate individuals will be selected for principal project activities based on the project outline or high-level brief. Managers may be recommending some project training. | 0%
Level-3 | 1-Management control | There is a consistent approach to project management controls across the organization, based on standard processes and methods. This standardization facilitates staff training and development and enables a common set of tools and other support arrangements to be deployed economically and effectively. The project lifecycle will not only focus on project initiation and development activities, but will also place equal emphasis on review and verification activities, implementation and handover. | 0%
Level-3 | 2-Benefits management | A centrally managed framework is used to define and track the delivery of benefits from the project outputs and in order to achieve the desired outcomes from delivered projects. Measures of success for projects are becoming defined and explicit. Post-project reviews are used to report formally on outcomes, and there may be procedures for periodic reviews of benefits after project closure. There will be a review of all qualitative benefits to ascertain whether these can be made more tangible and how they might be measured. | 0%
Level-3 | 3-Financial management | The organization will have established standards for the preparation of business cases and processes for the management of business cases throughout the project lifecycle. Project managers will monitor costs and expenditure in accordance with organizational guidelines and procedures, and there will be defined interfaces with other financial functions within the organization. SROs will have responsibility for each business case. Business cases are likely to be developed by iteration throughout the project lifecycle. | 0%
Level-3 | 4-Stakeholder management | The organization will have considered project management process improvement in the wider context of organizational improvement frameworks and approaches. A quality management approach will have been adopted and project improvement initiatives defined and managed as a change programme across the organization. Project management processes will be reviewed regularly and information made available to quality management. | 0%
Level-3 | 5-Risk management | Project risk management is conducted as a defined process that is cognizant of the organization’s policy for the management of risks. Inherent project risks are being minimized effectively through project initiation and planning stages, while acquired risks are identified throughout the project lifecycle and are either being eliminated or mitigated through viable contingency measures. Risks are being escalated to the appropriate levels within the organization, as necessary. | 0%
Level-3 | 6-Organizational governance | Project roles and responsibilities are explicitly documented within terms of reference, including those of governance and control, e.g. the project board. Strategic controls are being applied consistently, with decision-making structures in place. The governance arrangements for projects are clearly defined and embedded within the organization, although the value and benefit of these controls is not being fully realized. Stakeholder involvement is both planned and analysed, and the project manager confirms that stakeholder management is in place. | 0%
Level-3 | 7-Resource management | The organization has well-defined projects and project managers who are able to review and assess the resource requirements in relation to project delivery. Project managers will undertake sufficient planning to ascertain their project resource requirements. They will be able to highlight resource shortfalls and indicate individual/team training and development needs. The role of project manager will be a recognized skill within the organization, with an associated set of competencies. | 0%
Level-4 | 1-Management control | Project management is well aligned with the business plans and objectives. Project management has sufficient strategic importance for the organization to ensure that it is integrated with other business/strategic planning functions. Project management processes are fully embedded within the organization and there is a move towards more quantitative management and performance measurement. | 0%
Level-4 | 2-Benefits management | Benefits management is embedded within the project management approach. Projects can demonstrate strong business focus and strategic alignment. This will be documented in the business case. The organization will ensure that claimed benefits are realistic and that they are endorsed by the SRO. Systems will be in place to capture the measurement of benefits and collect information on benefit types. | 0%
Level-4 | 3-Financial management | The organization is able to prioritize investment opportunities effectively in relation to the availability of funds and other resources. Business cases are evaluated and investment decisions are ratified by the business. Project budgets are managed effectively and project performance against cost is monitored and compared. Cost models are used to demonstrate the efficacy of projects. | 0%
Level-4 | 4-Stakeholder management | The organization has established a continual improvement process by which lessons from previous projects are captured and embedded in new projects. There are quantitative goals for project management improvement across the organization. Improvement actions are tracked and measured across all projects, and necessary changes are planned and implemented. | 0%
Level-4 | 5-Risk management | Risk management is working effectively and the value of risk management can be demonstrated from the organizational perspective. Business stakeholders are comfortable with the management of project risks and their involvement, as appropriate, in that management process. Project managers are able to demonstrate integration between risk management and their planning and control mechanisms. | 0%
Level-4 | 6-Organizational governance | Decision-making processes associated with project performance adopt and adapt the broader organizational performance management and governance arrangements. Projects have explicit governance arrangements and clear channels of communication to ensure that stakeholders are informed and commitment remains high. | 0%
Level-4 | 7-Resource management | Resource management for projects is considered at a more strategic than tactical level within the organization. There is evidence of resource capacity management, through capacity planning. Resource availability and utilization are being measured and actions are taken to ensure the organization has the capacity and capability to meet its project delivery needs. | 0%
Level-5 | 1-Management control | Project management controls are being optimized to ensure that they are effective and efficient from the organizational perspective. They are regularly evaluated and enhanced so that they remain aligned with business imperatives, strategies and plans. Controls are not only used to monitor existing projects; the organization uses information feedback to proactively plan and design better control mechanisms for future projects. The level of control is planned in accordance with the criticality and complexity of the project to be managed. | 0%
Level-5 | 2-Benefits management | Benefits management is embedded within the organizational approach to change, and benefits being achieved are assessed as part of the development of corporate strategies. Projected benefits are fully documented in business cases in terms of a benefits management strategy that is fully supported by a benefits realization plan. Benefits network diagrams are likely to be in evidence to analyse dependencies. There is strong evidence that post-project reviews are performed and trends are established. Lessons are fed back into benefits realization planning and other management activities. | 0%
Level-5 | 3-Financial management | Project financial controls are fully integrated with those of the organization. Cost estimation techniques being used at the project level are continually reviewed in terms of actual vs. estimate comparisons to improve estimation throughout the organization. The organization will display effective cost analysis systems, in order to improve future project economy, efficiency and effectiveness. The organization will be able to demonstrate the value for money that is being achieved through its projects. | 0%
Level-5 | 4-Stakeholder management | Continual process improvement to the project management processes is undertaken in a planned manner across all projects,with demonstrable benefits and measurement of the efficacy of project management to the quality of projects. There is strong evidence of knowledge management and performance information being used to achieve improvement goals, with quantitative improvements in productivity, project quality and other measures. The organization has an established quality culture and is keen to contribute to best practice. | 0%
Level-5 | 5-Risk management | Risk management is embedded in the organizational culture and underpins all decision-making with respect to projects. Risk management will be integrated effectively with project planning and estimation, the project management control mechanisms, and the governance arrangements. There will be strong links with financial management processes, and any risks to project benefits will be highlighted and examined. Project managers will clearly demonstrate the value of risk management in terms of contingency budget savings. | 0%
Level-5 | 6-Organizational governance | The governance arrangements for projects are taken seriously by the organization, with demonstrable reporting lines to board level and with clear ownership, control and rew porting responsibilities embedded within the organization. The governance arrangements for all projects will be explicitly stated in relevant project documentation, including the business case. There will be evidence that these arrangements are periodically reviewed for effectiveness, based on lessons from project activity. | 0%
Level-5 | 7-Resource management | Resources are deployed optimally; there is clear evidence of load balancing and the effective use of both internal and external resources in accordance with a resource strategy. Project managers will have an understanding of the business processes and business objectives and will be able to assure senior managers that project resources are sufficiently focused on business needs. Resource managers are proactive in identifying future needs and in anticipating future criticality through, for example,technical time forecasting models. Succession plans are maintained for key positions. | 0%

## PjMP (Result)
P3M3 Model - Assessment Chart
Maturity Level | [7 empty] | Summary
Level 5 | [7 empty] | 0%
Level 4 | [7 empty] | 0%
Level 3 | [7 empty] | 0%
Level 2 | [7 empty] | 0%
Level 1 | [7 empty] | 0%
Process Perspectives
Fully Meets | Management Control | Benefits management | Financial management | Stakeholder management | Risk management | Organizational Governance | Resource management | PjM3 Final Assessment
Partially Meets | [7 empty] | Organization at PjM3 Maturity Level
Never Meets | [7 empty] | 0%

## P3M3 (Final Result)
P3M3 Model - Assessment Chart
Maturity Level | [7 empty] | Summary
Level 5 | [7 empty] | 0%
Level 4 | [7 empty] | 0%
Level 3 | [7 empty] | 0%
Level 2 | [7 empty] | 0%
Level 1 | [7 empty] | 0%
Process Perspectives
Fully Meets | Management Control | Benefits management | Financial management | Stakeholder management | Risk management | Organizational Governance | Resource management | P3M3 Final Assessment
Partially Meets | [7 empty] | Organization at P3M3 Maturity Level
Never Meets | [7 empty] | 0%